30-Day Sprint Plan (v2): Repositioned for the 2026 Market

Schedule: Mon-Fri, 3 hours/day = 60 hours total over 6 calendar weeks (Days 1-30 weekday-only)

New Positioning: "SaaS sales tax specialist for $5M-50M ARR companies — the human judgment layer above Anrok and below Big 4."

What's different from v1:

- Positioning sharpened against actual 2026 competitors (Anrok, Numeral, Zamp, Big 4)

- Channel partner strategy (fractional CFOs) starts Day 1, not Day 13

- AI tooling kept invisible — never lead with it in messaging

- Service line includes VDA + audit defense talking points (Anrok can't deliver these)

- Liability/credibility infrastructure built early, not patched on later

Goal at Day 30: First paid memo delivered (or signed engagement). 30+ prospects contacted. 3-5 fractional CFO partnership conversations active. Wiki covers SaaS in CA, TX, NY at production quality.

Week 1: Strategic Foundation + Positioning

Day 1 (Monday) — Lock Positioning, Don't Lock Features

Hour 1: Write your one-page positioning doc:

- Who I serve: SaaS companies, $5M-50M ARR, US-based, multi-state operations

- What I deliver: Strategic sales tax memos with primary-source citations — taxability analysis, nexus determinations, VDA strategy, audit defense

- What I'm not: A tax engine, a filing service, a chat interface, a replacement for Anrok/Numeral

- My differentiator: Human judgment on hard fact patterns, 48-hour turnaround, 1/4 the cost of Big 4

Hour 2: Draft your positioning statement against named competitors:

- vs. Anrok/Numeral: "They handle ongoing compliance. I handle the strategic questions their chat interfaces can't — VDAs, audits, complex bundles, M&A diligence."

- vs. Big 4: "They charge $400-800/hour with 2-3 week turnarounds. I deliver in 48 hours at fixed fees."

- vs. Generalist CPAs: "They don't specialize in SaaS sales tax. I do nothing else."

Hour 3: Set up Obsidian vault structure (states/, verticals/, memo-templates/, client-memos/, health-check/, partnerships/). Buy domain (yourname-salt.com or similar — keep it credible, not gimmicky).

Deliverable: Positioning doc that survives competitive scrutiny. Vault live. Domain owned.

Day 2 (Tuesday) — Liability & Credibility Infrastructure

Hour 1: Research professional liability (E&O) insurance options. Get 2-3 quotes — budget $1,500-3,000/year for $1M coverage. This is non-negotiable before delivering any paid memo.

Hour 2: Identify a SALT-credentialed reviewer for your first 10 memos. Options:

- A retired/semi-retired SALT consultant (post on LinkedIn, Pavilion, or via warm intros)

- A solo SALT attorney willing to do contract review at $200-300/memo

- A CMI (Certified Member, Institute for Sales and Use Tax) holder open to a side arrangement

This is critical — a credentialed name attached to your reviews removes 80% of credibility friction in early sales conversations.

Hour 3: Draft outreach messages to 5 potential reviewers. Send them.

Deliverable: Insurance quotes in hand. Reviewer search active.

Day 3 (Wednesday) — Memo Template + Wiki Schema

Hour 1: Build your master memo template in Obsidian. Sections: Question Presented, Short Answer, Facts, Authorities Considered (Primary + Secondary), State-by-State Analysis, Recommendations, Open Issues, Citations, Disclaimer.

Hour 2: Lock the wiki entry schema. Each entry has: Title, Last Verified Date, Verified By (you or reviewer), Primary Authority, Secondary Authority, Position Statement, Edge Cases, Open Questions, Related Entries, Recent Updates.

Hour 3: Build the metadata system — tag taxonomy by state, by vertical, by issue type, by complexity. This matters when wiki grows past 50 entries.

Deliverable: Memo template + wiki schema locked. Don't change these later.

Day 4 (Thursday) — California Wiki: First 2 Entries

Hour 1: Read CA CDTFA Reg. 1502 carefully (software taxability). Take notes in your own words first.

Hour 2: Use Claude to draft CA-SaaS-Taxability.md. Feed it the regulation + your notes. Verify every citation manually against the actual CDTFA text.

Hour 3: Use Claude to draft CA-Economic-Nexus.md (Cal. Rev. & Tax. Code § 6203). Verify citations.

Deliverable: 2 California entries built and citation-verified.

Day 5 (Friday) — California Edge Cases + Channel Strategy Foundation

Hour 1: Draft CA-Bundled-Transactions.md (handles SaaS + downloadable component edge case — this is the most common real-world question).

Hour 2: Build your fractional CFO target list. Search LinkedIn for "Fractional CFO SaaS" filter to people in US with 500+ connections. Aim for 30 names with profiles relevant to your buyer (SaaS focus, $5M-50M ARR clients).

Hour 3: Write 2 outreach message variants for fractional CFOs:

- Variant A (referral partnership angle): "I'm a SaaS sales tax specialist. Your clients hit nexus, you call me, I deliver memo, you get 15% referral. Want to chat?"

- Variant B (helpful angle): "I noticed your post about [SaaS finance topic]. I work specifically on SaaS sales tax. Happy to be a free resource if questions ever come up. No pitch."

Deliverable: California: 3 entries done. Channel partner list of 30 names with messages drafted.

Week 2: Texas + New York + First Outreach

Day 6 (Monday) — Texas Wiki Build

Hour 1: Read Tex. Tax Code § 151.0035 + 34 Tex. Admin. Code § 3.330 (data processing services). Texas's 80% rule is a critical piece of knowledge — get it deeply right.

Hour 2: Draft TX-SaaS-Taxability.md (data processing classification, 80% taxable basis). Verify citations.

Hour 3: Draft TX-Economic-Nexus.md (34 Tex. Admin. Code § 3.286 — $500K threshold, registration timing).

Deliverable: 2 Texas entries done.

Day 7 (Tuesday) — Texas Edge Cases + First CFO Outreach

Hour 1: Draft TX-Data-Processing-Edge-Cases.md (when SaaS isn't data processing, professional services bundling, custom development).

Hour 2: Send Variant B (helpful angle) to first 10 fractional CFOs. Don't pitch. Just introduce yourself and offer to be a resource.

Hour 3: Set up a simple tracking spreadsheet for outreach: Name, Company, Date Contacted, Variant Used, Response, Next Action.

Deliverable: Texas: 3 entries done. 10 CFO outreach messages sent.

Day 8 (Wednesday) — New York Wiki Build

Hour 1: Read N.Y. Tax Law § 1101(b)(6) + TSB-M-19(1)S. NY treats SaaS as prewritten software — fundamentally different from CA's view.

Hour 2: Draft NY-SaaS-Taxability.md. Note the prewritten classification and full taxability.

Hour 3: Draft NY-Economic-Nexus.md ($500K AND 100 transactions — conjunctive test, this catches people).

Deliverable: 2 New York entries done.

Day 9 (Thursday) — NY Edge Cases + Building Reviewer Pipeline

Hour 1: Draft NY-Customization-Exemption.md (when custom software escapes prewritten classification — meaningful for enterprise SaaS).

Hour 2: Follow up on Day 2 reviewer outreach. If no responses, send 5 more outreach messages to potential reviewers. You need this person locked in by Day 20.

Hour 3: Send 10 more fractional CFO messages (Days 7+9 = 20 contacted).

Deliverable: NY: 3 entries done. Reviewer pipeline expanded. 20 CFO contacts.

Day 10 (Friday) — Wiki Quality Pass + Service Lines

Hour 1: Re-verify 2 random citations from each state (CA, TX, NY). Fix any drift. Add cross-links between related entries.

Hour 2: Write your 4 service line descriptions (these become your sales conversation menu):

- Multi-State Taxability Memo ($2,500-4,500): SaaS taxability across 3-5 states with primary-source citations

- Economic Nexus Determination ($2,000-3,500): Where you've crossed thresholds, registration timing, exposure quantification

- VDA Strategy Memo ($4,500-8,000): Voluntary Disclosure Agreement analysis — which states, in what order, with what disclosure language

- Audit Defense Support ($3,500-12,000): Response to state audit notices, protest letter drafting, position memos

Hour 3: Update your positioning doc to reflect the four service lines clearly. Each one is something Anrok cannot deliver.

Deliverable: Wiki for CA/TX/NY at production quality (9 entries). Service menu locked.

Week 3: Skill Building + Engagement Infrastructure

Day 11 (Monday) — Build the Claude Project

Hour 1: Set up a new Claude Project. Upload all 9 wiki entries as project knowledge.

Hour 2: Write the system prompt for your "SaaS Sales Tax Memo Generator":

- Role definition (specialist analyst, not advisor)

- Citation discipline (every claim must cite primary authority from the wiki)

- Output format (your memo template, exactly)

- Refusal patterns (out-of-scope questions, jurisdictions not in wiki, federal income tax questions)

- Hallucination guardrails ("If you cannot find a primary authority in the project knowledge, do not invent one — flag the gap explicitly")

Hour 3: First test memo: "Northwind SaaS — taxability in CA + TX, $1.2M CA revenue, $650K TX revenue."

Deliverable: Working Claude Project. First test output generated.

Day 12 (Tuesday) — Skill Iteration

Hour 1: Run 3 more test memos with varied fact patterns: (a) pure SaaS hitting nexus in NY, (b) SaaS with downloadable component in CA + TX, (c) high-volume SaaS hitting nexus in all 3 states.

Hour 2: Compare outputs against your master memo template. Where did the skill fall short? Citation density? Recommendation specificity? Edge case handling?

Hour 3: Refine the system prompt based on observed failures. Re-run failing tests.

Deliverable: Skill produces consistently usable drafts.

Day 13 (Wednesday) — Engagement Letter, Disclaimer, Pricing

Hour 1: Draft your engagement letter. Include: scope of work, deliverable, fee, payment terms, what's NOT included, who can rely on the memo, term, mutual indemnification, signature blocks.

Hour 2: Draft your disclaimer language. Critical components: analytical purposes only, not legal/tax advice, requires independent verification, no attorney-client relationship, conclusions based on stated facts, no obligation to update for subsequent events.

Hour 3: Lock pricing for 4 service lines (from Day 10). Build a Google Form intake.

Deliverable: Legal documents drafted. Pricing live. Intake form active. Send documents to a lawyer for review by Day 20 (budget $500-1,500).

Day 14 (Thursday) — Direct Buyer Outreach Begins

Hour 1: Build your direct buyer target list: 20 SaaS founders/CFOs at $5M-50M ARR companies. Source: LinkedIn search, recent Series A/B announcements, SaaS-focused VC portfolio pages.

Hour 2: Write the buyer outreach message. Critical points:

- Lead with a specific insight, not your service ("Most SaaS companies miss that Texas's 80% rule means a $1M TX revenue company is paying tax on $800K")

- Reference their company specifically (one detail showing you researched them)

- Soft CTA ("I do focused work in this area — happy to chat if it ever becomes relevant")

- Never mention "AI" or "tool" — you're a specialist

Hour 3: Send first 10 buyer messages.

Deliverable: First 10 direct buyers contacted. Tracking sheet updated.

Day 15 (Friday) — Mid-Sprint Review + Fractional CFO Follow-Up

Hour 1: Mid-sprint retrospective. What's working? What's slow? Have any CFO responses come in? Has the reviewer search closed?

Hour 2: Follow up on Day 7+9 fractional CFO outreach with the 20 you've contacted. Replies that didn't go anywhere — send a one-line nudge with a specific recent insight.

Hour 3: Send 10 more buyer outreach messages (total: 20 buyers + 20 CFOs contacted).

Deliverable: Mid-sprint adjustments documented. Pipeline activity continuing.

Week 4: Convert Conversations + Deliver

Day 16 (Monday) — Discovery Call Mastery

Hour 1: Categorize all responses received so far. Buckets: Hot (wants a call), Warm (replied, uncommitted), Cold (silent). Aim for 3-5 calls scheduled this week.

Hour 2: Build your discovery call script. 20 minutes max. Sections: their current situation, what triggered their interest, what they've tried, scope of need, budget reality, timeline. Do not pitch in the first call. Listen.

Hour 3: Send 10 more outreach messages (mix buyers + CFOs) to keep pipeline fresh while early conversations close or stall.

Deliverable: Call script ready. Outreach pipeline at 50+ contacts.

Day 17 (Tuesday) — First Discovery Calls

Hour 1: Conduct 2 discovery calls (or block this time even if calls happen later in the day).

Hour 2: Post-call notes per prospect. What's their actual problem? What did they say about pricing? Did they mention Anrok or competitors?

Hour 3: For "yes-leaning" prospects, send tailored proposal: scope, deliverable, fee, timeline. Use Day 13 pricing as anchor; customize the scope language to their specific situation.

Deliverable: Real conversations happening. Proposals out within 24 hours of calls.

Day 18 (Wednesday) — More Discovery + Reviewer Confirmation

Hour 1: Conduct remaining discovery calls (2-3 more).

Hour 2: Confirm your SALT reviewer is locked in. Send them 2 sample wiki entries to review. Pay them for the review. Establish review process: you draft memo → reviewer checks before delivery → you incorporate feedback → final memo to client.

Hour 3: Follow up on outstanding proposals from Day 17. Answer questions. Do not discount below your floor — explain value instead.

Deliverable: Reviewer relationship operational. Proposals being negotiated.

Day 19 (Thursday) — First Signed Engagement (or Honest Assessment)

Hour 1: When the first "yes" comes — and one will, statistically, by Day 20-22 — send the engagement letter immediately. Get it signed via DocuSign or HelloSign. Take 50% deposit upfront.

If no "yes" yet by Day 19, conduct a brutal honesty exercise: Was the outreach quality? Was the messaging right? Was the pricing the friction? Talk to one of your Warm responses and ask directly: "What would have made this a yes?"

Hour 2: Either start work on Memo #1, or do another 10-message outreach push.

Hour 3: Update your wiki based on patterns from discovery calls — what questions came up that aren't yet covered? Add them as wiki gaps to fill in Week 5.

Deliverable: Either signed engagement OR data-driven adjustment. Both are wins if treated honestly.

Day 20 (Friday) — Lawyer Review + Insurance Lock-In

Hour 1: Get engagement letter and disclaimer reviewed by an attorney (likely scheduled this earlier, today is the close-out). Pay the bill ($500-1,500). Make any required changes.

Hour 2: Bind the E&O insurance policy. Get the certificate of insurance. You are now legally and professionally protected to deliver paid work.

Hour 3: If Memo #1 is in flight: complete first draft using the Claude Project, run citation verification, send to reviewer. If no engagement yet: send 15 more outreach messages and follow up on all warm leads with a specific value-adding insight.

Deliverable: Legal/insurance infrastructure complete. Memo #1 in production OR pipeline aggressively expanded.

Week 5: Deliver + Refine

Day 21 (Monday) — Memo #1 Delivery (if signed)

Hour 1: Reviewer feedback incorporated. Final review pass — read memo as if you were the client. Is the short answer actually clear?

Hour 2: Polish formatting. Convert to PDF. Write a 4-sentence delivery email summarizing key takeaways.

Hour 3: Send the memo. Invoice for the remaining 50%. Schedule a 30-minute walkthrough call for next week.

If no engagement signed yet: this is the day to seriously analyze what's broken. Pick up the phone (literally) with 2 warm prospects and ask why they haven't moved forward.

Deliverable: Memo #1 delivered OR root-cause analysis of pipeline stall.

Day 22 (Tuesday) — Post-Mortem + Walkthrough Prep

Hour 1: Honest retrospective on Memo #1 delivery (or the discovery process if no memo yet):

- Where did the system slow you down?

- Which wiki entries needed improvement?

- What did the client/prospect ask that you should have anticipated?

Hour 2: Update wiki and intake form based on gaps found.

Hour 3: Prep for client walkthrough call. Have a 2-page summary of findings + recommended next steps ready. Plan to ask for testimonial and 2 referrals at end of call.

Deliverable: System improvements committed. Walkthrough prep done.

Day 23 (Wednesday) — Walkthrough + Testimonial + Referrals

Hour 1: Conduct walkthrough call. Walk through findings, answer questions, identify next-step needs (registration, ongoing nexus monitoring, audit prep — refer out or quote separately).

Hour 2: End of call: ask "If this was useful, would you be willing to write a short testimonial?" Then: "Do you know 1-2 other SaaS founders who'd benefit from this kind of analysis?" This is where your business compounds.

Hour 3: Send recap email with testimonial request and referral asks in writing.

Deliverable: Testimonial request in motion. 1-2 warm referrals being requested.

Day 24 (Thursday) — Memo #2 OR Pipeline Acceleration

Hour 1-2: If Memo #2 signed, begin work. Same pipeline as Memo #1 (intake → fact-pattern analysis → Claude Project draft → reviewer → final delivery).

If no Memo #2 yet: deeper outreach push. 15 messages, focused on referral asks from any prior contacts.

Hour 3: Begin Illinois wiki entries (IL-SaaS-Taxability.md and IL-Chicago-Lease-Tax.md). Chicago's 9% lease tax is a memorable, valuable hook for content marketing — worth building before you have an IL client.

Deliverable: Either Memo #2 in flight or pipeline expanded. IL wiki started.

Day 25 (Friday) — First Content Marketing Asset

Hour 1: Draft a 600-word LinkedIn post: "The 9% sales tax most SaaS companies don't know they owe in Chicago." Use IL research as the hook. End with: "I help SaaS companies untangle this. DM me if you're approaching IL nexus or already there."

Hour 2: Post it. Engage with comments for 30 minutes. Connect with anyone who reacts substantively.

Hour 3: Draft 2 more post hooks based on what you've learned in client work (anonymized) — Texas 80% rule, NY's $1 conjunctive test catch, common bundling errors. Schedule for next week.

Deliverable: Public content presence started. Inbound channel slowly opening.

Week 6: Compound + Plan Forward

Day 26 (Monday) — First Monthly Health Check

Hour 1: Run your first staleness check. Review accumulated emails from CDTFA, TX Comptroller, NY DTF. Subscribe to Bloomberg State Tax Daily free trial if not done. Subscribe to Anrok's quarterly SaaS tax legislation update — your competitor publishes this for free, use it.

Hour 2: Check each wiki entry against any updates. Flag any drift. Update flagged entries. Note last-verified date. This is the differentiator you've been promising.

Hour 3: Document your health-check process as a repeatable checklist (what sources, what frequency, what triggers an update).

Deliverable: Wiki re-verified as fresh. Health check process documented.

Day 27 (Tuesday) — Productize Learnings

Hour 1: Review patterns across your discovery calls and any delivered memos. What do prospects consistently get wrong about their own situation?

Hour 2: Build a "SaaS Sales Tax Self-Assessment" — a 10-question diagnostic prospects can fill out. This becomes your top-of-funnel lead magnet. Questions like: "How many states do you have customers in? How many states do you have remote employees in? Do you bundle implementation services with subscriptions?" — each answer reveals nexus or taxability risk.

Hour 3: Build a simple Carrd or Notion landing page: positioning, 4 service lines, sample memo (anonymized), pricing ranges, intake form, self-assessment. Clean copy beats fancy design.

Deliverable: Self-assessment tool live. Landing page online.

Day 28 (Wednesday) — Outreach Scale-Up + Channel Partner Push

Hour 1: Send 15 outreach messages, now linking to your landing page and self-assessment.

Hour 2: Reach out to 5 more fractional CFOs with a more specific pitch now that you have a delivered memo (or detailed sample) to reference. Propose 15% referral fee on closed memos.

Hour 3: Conduct any discovery calls in pipeline. Send proposals same day.

Deliverable: Outreach volume up. Channel partner conversations advancing with proof points.

Day 29 (Thursday) — Memo Pipeline Work

Hour 1-2: If you have Memo #3 in progress, work it. If not, use this time to deepen wiki: add 2-3 edge-case entries (SaaS-Bundled-with-Implementation-Services.md, SaaS-Marketplace-Facilitator-Rules.md).

Hour 3: Continue outreach and follow-ups.

Deliverable: Either revenue progressing or wiki getting deeper.

Day 30 (Friday) — 30-Day Retrospective + Honest Strategic Decision

Hour 1: Write your honest retrospective:

- Revenue generated (memos delivered × price)

- Pipeline value (active proposals × close rate estimate)

- Hours spent vs. hours billed (your effective rate)

- Wiki growth (entries, citations verified)

- Channel partnerships forming

- What's working / what's broken

Hour 2: Make the strategic decision based on actual data:

- Revenue flowing ($3K+ delivered, $5K+ pipeline): Sprint 2 focuses on scaling — channel partnerships, content, possibly a 4th state

- Revenue slow (1 memo or zero, but real conversations happening): Sprint 2 focuses on conversion — deeper qualification, sharper proposals, maybe pricing test

- Revenue zero AND no real conversations: Sprint 2 focuses on positioning — the offer or audience is wrong; talk to 10 prospects about why they aren't buying before changing anything

Hour 3: Plan Days 31-45. Specific goals, specific tactics, specific metrics. Don't plan in detail until you have Day 30 data.

Deliverable: Honest assessment. Clear next sprint plan.

What Success Looks Like at Day 30 (Realistic Ranges)

Most likely (60% of focused attempts):

- 1-2 paid memos delivered or signed ($2K-7K revenue)

- 4-6 prospects in active pipeline

- 1 testimonial in hand or being requested

- 2-3 fractional CFO partnership conversations active

- Wiki at 12-15 entries across 3-4 states

- Reviewer relationship operational

- Insurance and legal infrastructure complete

- Clear signal that the model works, with specific friction points to address

Optimistic (25%):

- 3-4 paid memos delivered ($7K-15K revenue)

- 8-10 prospects in pipeline

- 2-3 testimonials

- 1 referral partnership signed

- Considering pricing increase

Pessimistic (15%):

- 0 paid memos

- 1-2 lukewarm prospects

- Lots of "interesting, let me think" responses

- You need to seriously rethink positioning, vertical sub-segment, or pricing

All three outcomes are useful information. Pessimistic is data telling you to adjust before sinking more time. Most successful specialists went through a soft Day 30 and recalibrated.

What's Different About This Plan vs. v1

Five concrete shifts based on the competitive intelligence:

- Reviewer relationship locked in by Day 20 — credibility infrastructure, not an afterthought

- Channel partner outreach starts Day 5 — fractional CFOs are your highest-leverage channel

- Service line expanded to 4 deliverables — VDA and audit defense are your moat against Anrok

- Liability infrastructure (insurance, lawyer review) before any paid delivery — protects everything

- AI tooling stays invisible in messaging — never mentioned in client-facing communication

The Five Things You Cannot Skip

These are the survival items. Everything else can flex.

- Get insurance before delivering paid work (Day 20)

- Lock in a credentialed reviewer (by Day 20)

- Get legal documents reviewed by an attorney (by Day 20)

- Do not position as "AI-powered" in any client communication

- Verify every citation manually before any memo leaves your hands

Skip these and you're not building a business — you're building a liability.

What's Coming in Days 31-60 (Preview)

Based on what Day 30 reveals, the next sprint likely includes:

- Adding 2 more states (WA + one based on client demand)

- Expanding into Florida if multiple clients ask (no income tax state, but huge SaaS hub)

- Building VDA-specific service playbook (highest-margin work)

- First substantive content asset (state-by-state SaaS taxability comparison guide as lead magnet)

- Pricing test on next 3 clients (raise to top of range)

- Fractional CFO partnership formalization with one or two best-fit partners

But plan that sprint after you have Day 30 data — not before.

One Final Honest Note

Days 16-22 will feel emotionally hard. You'll send messages and get ignored. Some prospects will tell you they "use Anrok for everything" without understanding what you actually do. A few will challenge your pricing. This is normal in this market. Anrok has $100M+ in venture funding to make their voice louder than yours. Your edge is depth, judgment, and human relationships — none of which scale through ads, but all of which compound through repeat work and referrals.

Block your 3 hours on a calendar daily. Treat it like a real job. Show up especially on the days you don't feel like it. That's the differentiator nobody else can replicate.

Want me to draft the actual outreach messages (both for fractional CFOs and direct SaaS buyers) and the discovery call script as concrete copy you can use starting Day 5? Those are the two pieces of friction that slow most people down — having them written and ready in advance saves 5-10 hours and improves response rates materially.

You've used 75% of your weekly limit